## Budget
Project ID | Project | Stage | Approved Budget
101 | Skyline Towers | 03 - Construction | 54454403.364
101 | Skyline Towers | 01 - Land | 13895841.088
101 | Skyline Towers | 02 - Design | 12112994.861
102 | Harbor View Residences | 03 - Construction | 24724044.484
102 | Harbor View Residences | 01 - Land | 6309157.239
102 | Harbor View Residences | 02 - Design | 9059367.392
103 | Granite Gardens | 03 - Construction | 85131754.514
103 | Granite Gardens | 01 - Land | 17442839.146
103 | Granite Gardens | 02 - Design | 23166666.667
104 | Emerald Estates | 03 - Construction | 55477928.446
104 | Emerald Estates | 01 - Land | 18380450.573
104 | Emerald Estates | 02 - Design | 12463996.75
105 | Crestview Commercial Complex | 03 - Construction | 61725931.392
105 | Crestview Commercial Complex | 01 - Land | 23949845.708
105 | Crestview Commercial Complex | 02 - Design | 15072050.411

## Consumption
Project ID | Date | Amount | Stage | Contract Ref
105 | 2020-07-01 | 1021490.9677 | 01 - Land | CR-1000
105 | 2020-10-20 | 1080195.2657 | 01 - Land | CR-1785
105 | 2020-07-03 | 765357.5969 | 01 - Land | CR-2029
105 | 2020-07-10 | 1364383.2649 | 01 - Land | CR-2365
105 | 2020-05-05 | 2453412.0544 | 01 - Land | CR-2976
105 | 2020-05-18 | 700796.3345 | 01 - Land | CR-3105
105 | 2020-11-14 | 153453.3111 | 01 - Land | CR-4573
105 | 2020-12-02 | 776442.8246 | 01 - Land | CR-4643
105 | 2020-11-14 | 1323402.6022 | 01 - Land | CR-4737
105 | 2020-12-26 | 1087751.706 | 01 - Land | CR-5185
105 | 2020-06-10 | 3881148.7233 | 01 - Land | CR-6360
105 | 2020-03-30 | 1336637.3467 | 01 - Land | CR-6837
105 | 2020-06-13 | 2913438.2143 | 01 - Land | CR-7651
105 | 2020-06-18 | 1330416.2512 | 01 - Land | CR-8896
105 | 2020-01-18 | 1764557.8335 | 01 - Land | CR-9114
105 | 2020-04-19 | 1979059.5431 | 01 - Land | CR-9284
104 | 2020-04-05 | 1592692.4887 | 01 - Land | CR-1042
104 | 2020-04-19 | 2243389.9742 | 01 - Land | CR-2747
104 | 2020-12-30 | 1083408.5904 | 01 - Land | CR-4076
104 | 2020-05-10 | 4642871.6349 | 01 - Land | CR-4460
104 | 2020-10-28 | 654898.6939 | 01 - Land | CR-5076
104 | 2020-02-27 | 2450496.1287 | 01 - Land | CR-6418
104 | 2020-01-06 | 775999.9558 | 01 - Land | CR-6642
104 | 2020-09-24 | 2435902.9055 | 01 - Land | CR-7554
104 | 2020-06-20 | 2527874.7414 | 01 - Land | CR-7717
104 | 2020-07-16 | 742764.8865 | 01 - Land | CR-8429
103 | 2020-09-24 | 7214773.9903 | 01 - Land | CR-1128
103 | 2020-10-10 | 2123587.6803 | 01 - Land | CR-5301
103 | 2020-02-21 | 1685729.4713 | 01 - Land | CR-6223
103 | 2020-03-07 | 527060.9293 | 01 - Land | CR-6394
103 | 2020-02-07 | 764928.5276 | 01 - Land | CR-6444
103 | 2020-06-12 | 799059.7467 | 01 - Land | CR-6454
103 | 2020-04-21 | 2398702.0299 | 01 - Land | CR-6928
103 | 2020-06-07 | 1642166.6246 | 01 - Land | CR-8841
102 | 2020-07-16 | 729892.6437 | 01 - Land | CR-2667
102 | 2020-12-01 | 315301.523 | 01 - Land | CR-2959
102 | 2020-11-21 | 1991407.2966 | 01 - Land | CR-3593
102 | 2020-11-04 | 409145.3483 | 01 - Land | CR-4003
102 | 2020-10-01 | 673050.6455 | 01 - Land | CR-4122
102 | 2020-08-06 | 1054470.8536 | 01 - Land | CR-5235
102 | 2020-10-22 | 682569.1404 | 01 - Land | CR-5465
102 | 2020-10-20 | 733846.441 | 01 - Land | CR-5481
102 | 2020-06-13 | 264210.3421 | 01 - Land | CR-6883
102 | 2020-03-03 | 732925.7659 | 01 - Land | CR-6900
101 | 2020-05-28 | 916641.5787 | 01 - Land | CR-1003
101 | 2020-11-07 | 1842243.4477 | 01 - Land | CR-1216
101 | 2020-06-20 | 1558885.5731 | 01 - Land | CR-2303
101 | 2020-08-17 | 793837.7383 | 01 - Land | CR-3793
101 | 2020-01-16 | 5296227.5238 | 01 - Land | CR-3857
101 | 2020-08-30 | 977489.1689 | 01 - Land | CR-5406
101 | 2020-12-21 | 877583.2901 | 01 - Land | CR-6324
101 | 2020-08-27 | 458318.3139 | 01 - Land | CR-6501
101 | 2020-08-09 | 1598973.3653 | 01 - Land | CR-8488
105 | 2021-06-21 | 103903.3473 | 02 - Design | CR-1395
105 | 2022-01-20 | 760666.5265 | 02 - Design | CR-1740
105 | 2022-03-31 | 1428255.5536 | 02 - Design | CR-2072
105 | 2021-03-14 | 1016349.5424 | 02 - Design | CR-2495
105 | 2022-06-06 | 331528.1271 | 02 - Design | CR-2991
105 | 2021-03-13 | 1891958.4594 | 02 - Design | CR-3424
105 | 2021-03-03 | 3048392.1885 | 02 - Design | CR-4326
105 | 2021-04-29 | 667958.7334 | 02 - Design | CR-5407
105 | 2021-02-20 | 1380078.2905 | 02 - Design | CR-7153
105 | 2022-05-28 | 693496.4351 | 02 - Design | CR-7353
105 | 2021-09-30 | 2742054.6654 | 02 - Design | CR-7976
105 | 2021-07-19 | 1484858.1308 | 02 - Design | CR-9296
104 | 2021-12-03 | 1220735.2092 | 02 - Design | CR-2386
104 | 2022-05-15 | 1447462.2084 | 02 - Design | CR-2823
104 | 2021-12-22 | 1838803.5044 | 02 - Design | CR-3839
104 | 2021-05-01 | 684631.1922 | 02 - Design | CR-5176
104 | 2021-11-30 | 211723.0865 | 02 - Design | CR-5373
104 | 2021-08-25 | 1826184.072 | 02 - Design | CR-6206
104 | 2022-02-08 | 1437131.3052 | 02 - Design | CR-6613
104 | 2022-01-11 | 910665.3448 | 02 - Design | CR-7473
104 | 2022-03-27 | 390795.9423 | 02 - Design | CR-7634
104 | 2022-01-24 | 849128.4243 | 02 - Design | CR-7814
104 | 2021-03-09 | 807016.1953 | 02 - Design | CR-8669
104 | 2021-07-04 | 696073.5154 | 02 - Design | CR-9045
103 | 2021-10-24 | 1688412.7894 | 02 - Design | CR-2030
103 | 2021-01-03 | 2522955.0817 | 02 - Design | CR-2516
103 | 2021-11-06 | 3270940.2065 | 02 - Design | CR-3506
103 | 2021-03-02 | 814266.4371 | 02 - Design | CR-4241
103 | 2021-10-17 | 2683556.6578 | 02 - Design | CR-4255
103 | 2021-01-10 | 2179305.2738 | 02 - Design | CR-4689
103 | 2021-07-25 | 1933246.6028 | 02 - Design | CR-5707
103 | 2021-03-01 | 1267277.1294 | 02 - Design | CR-6881
103 | 2021-02-03 | 3316013.5302 | 02 - Design | CR-7145
103 | 2021-04-07 | 624125.5328 | 02 - Design | CR-7502
103 | 2021-07-05 | 2549724.2286 | 02 - Design | CR-8437
102 | 2022-04-10 | 858127.9609 | 02 - Design | CR-1225
102 | 2021-04-03 | 1260754.4329 | 02 - Design | CR-2511
102 | 2021-12-08 | 904267.3448 | 02 - Design | CR-2606
102 | 2021-06-06 | 1054996.617 | 02 - Design | CR-4513
102 | 2022-06-29 | 619504.4 | 02 - Design | CR-4659
102 | 2021-11-11 | 828022.0065 | 02 - Design | CR-5774
102 | 2021-02-27 | 273243.9814 | 02 - Design | CR-8250
102 | 2021-12-11 | 216323.2387 | 02 - Design | CR-8528
102 | 2022-06-18 | 281398.4595 | 02 - Design | CR-8563
102 | 2021-01-05 | 1214070.9864 | 02 - Design | CR-8839
102 | 2022-04-26 | 446283.4649 | 02 - Design | CR-9227
102 | 2021-01-21 | 1067427.1069 | 02 - Design | CR-9836
101 | 2021-08-21 | 986642.7365 | 02 - Design | CR-1292
101 | 2022-02-11 | 685890.684 | 02 - Design | CR-1814
101 | 2021-11-20 | 1096406.3116 | 02 - Design | CR-2025
101 | 2021-05-02 | 760546.5162 | 02 - Design | CR-4473
101 | 2022-04-25 | 1308705.8656 | 02 - Design | CR-4671
101 | 2021-08-10 | 543453.5385 | 02 - Design | CR-5089
101 | 2021-05-21 | 60418.9474 | 02 - Design | CR-6925
101 | 2021-09-01 | 1434440.4695 | 02 - Design | CR-8316
101 | 2022-02-01 | 1390208.6201 | 02 - Design | CR-8477
101 | 2022-01-11 | 458151.3049 | 02 - Design | CR-8584
101 | 2021-03-13 | 1842301.5985 | 02 - Design | CR-9091
101 | 2022-04-22 | 754639.9726 | 02 - Design | CR-9567
101 | 2022-03-16 | 1832393.4345 | 02 - Design | CR-9871
105 | 2023-02-22 | 1450617.4292 | 03 - Construction | CR-1109
105 | 2022-11-11 | 2450652.7817 | 03 - Construction | CR-1342
105 | 2023-02-01 | 1281875.3522 | 03 - Construction | CR-1618
105 | 2023-01-25 | 2021012.867 | 03 - Construction | CR-3217
105 | 2023-03-20 | 1997522.7716 | 03 - Construction | CR-3308
105 | 2023-07-25 | 1840260.9802 | 03 - Construction | CR-4148
105 | 2023-09-18 | 968139.5442 | 03 - Construction | CR-4178
105 | 2022-01-17 | 1347794.0062 | 03 - Construction | CR-5255
105 | 2023-10-05 | 873005.8353 | 03 - Construction | CR-5449
105 | 2022-09-28 | 275009.9437 | 03 - Construction | CR-6383
105 | 2022-03-06 | 1506279.9709 | 03 - Construction | CR-7103
105 | 2022-04-01 | 1323038.5177 | 03 - Construction | CR-8620
104 | 2022-04-11 | 5669047.2613 | 03 - Construction | CR-2396
104 | 2023-05-14 | 6935322.8357 | 03 - Construction | CR-2562
104 | 2023-09-18 | 5228215.3521 | 03 - Construction | CR-2901
104 | 2023-10-19 | 5052960.5966 | 03 - Construction | CR-4488
104 | 2022-09-25 | 4412971.0855 | 03 - Construction | CR-5171
104 | 2023-05-05 | 2589076.2358 | 03 - Construction | CR-5426
104 | 2022-12-30 | 6984255.5487 | 03 - Construction | CR-5436
104 | 2023-07-28 | 4988817.703 | 03 - Construction | CR-7373
104 | 2022-07-15 | 5104023.6914 | 03 - Construction | CR-7897
104 | 2023-09-04 | 4876193.0634 | 03 - Construction | CR-7948
104 | 2023-03-18 | 103780.1066 | 03 - Construction | CR-7967
103 | 2022-06-16 | 9895758.7752 | 03 - Construction | CR-1383
103 | 2023-06-20 | 12161453.2925 | 03 - Construction | CR-1744
103 | 2023-04-13 | 5261813.8558 | 03 - Construction | CR-5524
103 | 2022-02-05 | 3125547.1518 | 03 - Construction | CR-5761
103 | 2023-05-30 | 4448769.4576 | 03 - Construction | CR-6151
103 | 2023-09-22 | 10605755.9369 | 03 - Construction | CR-6493
103 | 2022-02-28 | 10553276.8198 | 03 - Construction | CR-7608
103 | 2022-11-30 | 821208.9657 | 03 - Construction | CR-7859
103 | 2023-04-10 | 9252887.6975 | 03 - Construction | CR-8291
103 | 2022-08-26 | 10194968.6851 | 03 - Construction | CR-8353
103 | 2023-07-20 | 8165654.8622 | 03 - Construction | CR-9071
102 | 2022-05-10 | 1360127.7773 | 03 - Construction | CR-1358
102 | 2023-08-26 | 1450913.9394 | 03 - Construction | CR-1835
102 | 2022-01-12 | 114380.2473 | 03 - Construction | CR-4161
102 | 2023-03-03 | 3361554.4704 | 03 - Construction | CR-4412
102 | 2022-05-22 | 1178404.6492 | 03 - Construction | CR-5107
102 | 2022-01-09 | 2169242.4457 | 03 - Construction | CR-5174
102 | 2023-06-09 | 2010481.5962 | 03 - Construction | CR-5247
102 | 2022-04-03 | 3241459.31 | 03 - Construction | CR-5251
102 | 2022-07-24 | 1909625.7492 | 03 - Construction | CR-7160
102 | 2022-12-16 | 1307497.2892 | 03 - Construction | CR-7703
102 | 2022-11-24 | 2523569.2507 | 03 - Construction | CR-8017
102 | 2022-04-29 | 3243021.2224 | 03 - Construction | CR-8168
102 | 2023-03-29 | 2233952.0531 | 03 - Construction | CR-9787
101 | 2023-05-16 | 771374.1643 | 03 - Construction | CR-1640
101 | 2022-06-12 | 6392.951 | 03 - Construction | CR-1724
101 | 2022-06-04 | 736957.3517 | 03 - Construction | CR-1793
101 | 2022-06-11 | 506357.677 | 03 - Construction | CR-1966
101 | 2023-02-11 | 183627.6637 | 03 - Construction | CR-2211
101 | 2022-12-05 | 354841.278 | 03 - Construction | CR-3307
101 | 2023-09-16 | 665209.446 | 03 - Construction | CR-3603
101 | 2023-03-20 | 319063.777 | 03 - Construction | CR-3927
101 | 2022-08-09 | 201009.0791 | 03 - Construction | CR-5498
101 | 2022-11-22 | 514517.3679 | 03 - Construction | CR-5890
101 | 2023-05-26 | 216720.6479 | 03 - Construction | CR-6003
101 | 2022-03-08 | 647250.1244 | 03 - Construction | CR-7481
101 | 2023-03-15 | 252548.4719 | 03 - Construction | CR-7845
103 | 2023-04-07 | 674125.5328 | 02 - Design | CR-7502
103 | 2023-07-05 | 2549724.2286 | 02 - Design | CR-8437